## 1.40.20 QC Topographic Data
| 1.40.20 QC Topographic Data | [5 empty] | Yes | C
[7 empty] | No | D
| Project Name | Central TX |  | Dewberry Project Number | 50036727 |  | N/A | N
| Product Being Reviewed | Classified LAS, Breaklines, Metadata |  | URS Project Number | 15725026.0042
| Print Date | 2011-09-22 |  | Review Type | Independent Technical Review
| Reviewer(s) | Stephen DiCicco
| Review Item | Yes No N/A | Reviewer Comment(s) | Originator Disposition * | Originator Response | Reviewer Verification (initials)
Detail Check Verification
| Detail check was conducted | Yes | The detail check was conducted by URS
| Approved reviewer(s) were used for the detail check | Yes | Harold Rempel and Jesse Pinchot completed the review
| All comments from detail check have been properly addressed | NO | Metadata contains validation errors
Terrain
Topo Data
| Review of Detail Check checklist indicates that data meets project specifications and usability | Yes | Detail Check did not indicate any issues that would cause the project to not meet specifications and usability
GeoTerrain
| Review of final Digital Terrain Model shows that it meets project specifications and usability | N/A | No terrain submitted
TSDN
| Correct template was used | N/A | No TSDN submitted
| Certification of Compliance form is signed (Figure M-11 in Appendix M) | N/A | No TSDN submitted
| Files for MIP upload follow Appendix M folder structure | N/A | No TSDN submitted
| Spelling and grammar are correct | N/A | No TSDN submitted
| Typos are eliminated | N/A | No TSDN submitted
| All figures, tables and exhibits are included | N/A | No TSDN submitted
| All tables are in numerical order and all title block and frame information is correct | N/A | No TSDN submitted
| Pagination matches the table of contents | N/A | No TSDN submitted
Other Review Items (add rows as needed)
Metadata produced 5 errors from USGS Metadata Validation Service
| * Disposition Codes | C = Will Comply; D = Delete Comment; N = Incorporate in Next Submittal
Comments (this section not to be used for QC calls)
Originator Signature: |  | ____________________________________________ |  | Date: | ____________________
Reviewer Signature: |  | ____________________________________________ |  | Date: | 2011-09-23
Task Order/Study Manager Signature: |  | ____________________________________________ |  | Date: | ____________________